## Sheet1
| Project start date | 2024-12-05 | [5 empty] | 2024-12-12 |  |  |  | 2025-01-09 |  |  |  | 2025-02-06 |  |  |  |  | 2025-03-13 |  |  |  | 2025-04-10 |  |  |  | 2025-05-08 |  |  |  |  | 2025-06-05 |  |  |  | 2025-07-10 |  |  |  | 2025-08-07 |  |  |  |  | 2025-09-11 |  |  |  | 2025-10-09 |  |  |  | 2025-11-06
[8 empty] | 2024-12-12 |  |  |  | 2025-01-09 |  |  |  | 2025-02-06 |  |  |  |  | 2025-03-13 |  |  |  | 2025-04-10 |  |  |  | 2025-05-08 |  |  |  |  | 2025-06-12 |  |  |  | 2025-07-10 |  |  |  | 2025-08-07 |  |  |  |  | 2025-09-11 |  |  |  | 2025-10-09 |  |  |  | 2025-11-06
| Project name | [5 empty] | Week starting | time axis 2024-12-05 to 2025-11-27
# | Activity | AssignedTo | Start | End | Days | Status | % Done
1 | task 1 | Me | 2024-12-05 | 2024-12-13 | 7 | In progress | 50% | bar: 2024-12-12
2 | task 2 | Me | 2024-12-13 | 2024-12-28 | 11 | Blocked | 35% | bar: 2024-12-26
3 | task 3 | Me | 2024-12-28 | 2025-01-19 | 15 | In progress | 20% | bar: 2025-01-16
4 | task 4 | Me | 2024-12-15 | 2024-12-23 | 6 | In progress | 2% | bar: 2024-12-19
5 | task 5 | Me | 2024-12-23 | 2024-12-31 | 7 | Complete | 90% | bar: 2024-12-26
6 | task 6 | Me | 2024-12-31 | 2025-01-22 | 17 | In progress | 1% | bar: 2025-01-16
7 | task 7 | Me | 2025-01-22 | 2025-02-06 | 12 | Blocked | 2% | bar: 2025-02-06
8 | task 8 | Me | 2025-02-06 | 2025-02-21 | 12 | In progress | 1% | bar: 2025-02-20
9 | task 9 | Me | 2025-02-21 | 2025-03-01 | 6 | In progress | 2% | bar: 2025-02-27
10 | task 10 | Me | 2025-01-23 | 2025-02-07 | 12 | Blocked | 3% | bar: 2025-02-06
11 | task 11 | Me | 2025-02-07 | 2025-02-15 | 6 | Not started | 0% | bar: 2025-02-13
|  | add milestone | Add gnt bars stp 1-2 |  | compl frml | block frml
| formulas=> | FALSE | TRUE | TRUE | FALSE | FALSE
statuses
| Not started |  |  |  | blocked
| In progress |  |  |  | completed
Blocked
Complete
https://youtu.be/tuQpGzL_14g?si=7MaH7WiYTP2mfML9
https://youtu.be/un8j6QqpYa0?si=JURjzfcLpNJBImrf
Formulas:
Start = [End, row above]
End = [Start]+8
Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Sheet2
PROJECT: |  | Code Language Translation Plugin: Bridging English and French Programming Collaboration
Project Start Date: |  |  | 2024-12-07 | [6 empty] | 2024-12-09 | [12 empty] | 2025-01-04
[10 empty] | 2024-12-09 | [12 empty] | 2025-01-04 | [14 empty] | 2025-02-03 | [13 empty] | 2025-03-03
 | time axis 2024-12-07 to 2025-03-31
No | Activity |  |  | AssignedTo | Start | End | Days | Status | % Done
1 | Research and Planning |  |  | Me
1-1 | Define Scope and Requirements |  |  | - | 2024-12-07 | 2024-12-09 | 1 | In progress | 50%
1-2 | Research NLP Libraries and Translation |  |  | - | 2024-12-10 | 2024-12-17 | 6 | Not started | 0% | bar: 2024-12-07
1-3 | Design Plugin Architecture |  |  | - | 2024-12-18 | 2024-12-23 | 4 | In progress | 50%
2 | Development |  |  | Me
2-1 | Backend Script Development |  |  | -
2-1-1 | Set Up Development Environment |  |  | - | 2024-12-24 | 2024-12-26 | 3 | Not started | 0%
2-1-2 | Develop Basic Code Parser |  |  | - | 2024-12-26 | 2025-01-09 | 11 | Not started | 0%
2-1-3 | Implement Translation Layer |  |  | - | 2025-01-09 | 2025-01-14 | 4 | Not started | 0%
2-1-4 | Build Output Generator |  |  | - | 2025-01-14 | 2025-01-19 | 4 | Not started | 0%
2-2 | IDE Integration |  |  | -
2-2-1 | Design IDE Plugin Interface |  |  | - | 2025-01-20 | 2025-01-25 | 5 | Not started | 0%
2-2-2 | Implement Real-Time Translation Feature |  |  | - | 2025-01-25 | 2025-02-08 | 10 | Not started | 0%
2-2-3 | Add User Customization Options |  |  | - | 2025-02-08 | 2025-02-15 | 5 | Not started | 0%
3 | Testing and Finalization |  |  | Me
3-1 | Unit Testing for Backend Script |  |  | - | 2025-02-16 | 2025-02-21 | 5 | Not started | 0%
3-2 | Integration Testing with IDEs |  |  | - | 2025-02-21 | 2025-02-25 | 3 | Not started | 0%
3-3 | User Testing and Feedback |  |  | - | 2025-02-25 | 2025-03-01 | 4 | Not started | 0%
3-4 | Documentation and Deployment |  |  | - | 2025-03-01 | 2025-03-04 | 2 | Not started | 0%
statuses |  |  | statues | TRUE
Not started |  |  | Not started
In progress |  |  | In progress
Blocked |  |  | Blocked
Complete |  |  | Complete
Formulas:
Start = [End, row above]+1
Start = [End, row above]
End = [Start]+2
End = [End, row above]+4
Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Sheet3
PROJECT: |  | Code Language Translation Plugin: Bridging English and French Programming Collaboration
Project Start Date: |  |  | 2024-12-07
[10 empty] | 2024-12-01 | [6 empty] | 2024-12-08 | [6 empty] | 2024-12-15 | [6 empty] | 2024-12-22 | [6 empty] | 2024-12-29 | [6 empty] | 2025-01-05 | [6 empty] | 2025-01-12 | [6 empty] | 2025-01-19 | [6 empty] | 2025-01-26 | [6 empty] | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02 | [6 empty] | 2025-03-09 | [6 empty] | 2025-03-16 | [6 empty] | 2025-03-23
 | time axis 2024-12-01 to 2025-03-29
No | Activity |  |  | AssignedTo | Start | End | Days | Status | % Done | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Research and Planning |  |  | Me
1-1 | Define Scope and Requirements |  |  | - | 2024-12-07 | 2024-12-09 | 1 | In progress | 50%
1-2 | Research NLP Libraries and Translation |  |  | - | 2024-12-10 | 2024-12-17 | 6 | Not started | 45%
1-3 | Design Plugin Architecture |  |  | - | 2024-12-18 | 2024-12-23 | 4 | In progress | 50%
2 | Development |  |  | Me
2-1 | Backend Script Development |  |  | -
2-1-1 | Set Up Development Environment |  |  | - | 2024-12-24 | 2024-12-26 | 3 | Not started | 0%
2-1-2 | Develop Basic Code Parser |  |  | - | 2024-12-26 | 2025-01-09 | 11 | Not started | 0%
2-1-3 | Implement Translation Layer |  |  | - | 2025-01-09 | 2025-01-14 | 4 | Not started | 0%
2-1-4 | Build Output Generator |  |  | - | 2025-01-14 | 2025-01-19 | 4 | Not started | 0%
2-2 | IDE Integration |  |  | -
2-2-1 | Design IDE Plugin Interface |  |  | - | 2025-01-20 | 2025-01-25 | 5 | Not started | 0%
2-2-2 | Implement Real-Time Translation Feature |  |  | - | 2025-01-25 | 2025-02-08 | 10 | Not started | 0%
2-2-3 | Add User Customization Options |  |  | - | 2025-02-08 | 2025-02-15 | 5 | Not started | 0%
3 | Testing and Finalization |  |  | Me
3-1 | Unit Testing for Backend Script |  |  | - | 2025-02-16 | 2025-02-21 | 5 | Not started | 0%
3-2 | Integration Testing with IDEs |  |  | - | 2025-02-21 | 2025-02-25 | 3 | Not started | 0%
3-3 | User Testing and Feedback |  |  | - | 2025-02-25 | 2025-03-01 | 4 | Not started | 0%
3-4 | Documentation and Deployment |  |  | - | 2025-03-01 | 2025-03-04 | 2 | Not started | 0%